## Sheet1
Date | No. | Decision or Action or Message | Responsible | Status
2021-03-05 | 1 | Identify possible designs/design elements for the redeisgn of the travel agency website. | Jinyi | Complete
2021-03-05 | 2 | Create initial mockup/template of travel agency website based on design suggestions from research and upload to GitHub. | Tamika | Complete
2021-03-05 | 3 | Based on the mockup design, develop the index page for the Travel Canada site using HTML, CSS & JavaScript and upload to GitHub. | Jonn | Complete
2021-03-08 | 4 | Trouble shoot "jumbotron-link-desc-container" section of index page, so that elements layer and not stack. | Jinyi | Complete
2021-03-08 | 5 | Look into evolving index page to include links to Flights, Hotels, and Rentals for each destination. | Tamika | N/A
2021-03-08 | 6 | Bring in contact page from initial project and re-design it to fit current design and feel of overall site. | Oswaldo | Open
2021-03-08 | 7 | Design and develop About Page for the Travel Canada site ensuring fit with overall theme of site. | Jonn | Open
2021-03-10 | 8 | Create Montreal webpage based on established template and upload to GitHub. | Jinyi | Open
2021-03-10 | 9 | Create Toronto webpage based on established template and upload to GitHub. | Oswaldo | Open
2021-03-10 | 10 | Create Calgary webpage based on established template and upload to GitHub. | Jonn | Open
11
12
13
14
15
16
17
18
19
20
21
22
23
24
Note on E7: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Not required at this time.