## Sheet1
Date | No. | Decision or Action or Message | Responsible | Status
2021-03-05 | 1 | Identify possible designs/design elements for the redeisgn of the travel agency website. | Jinyi | Complete
2021-03-05 | 2 | Create initial mockup of travel agency website based on design suggestions from research. | Tamika | Complete
2021-03-05 | 3 | Based on the mockup design, develop the index page for the Travel Canada site using HTML, CSS & JavaScript. | Jonn | Complete
2021-03-08 | 4 | Trouble shoot "jumbotron-link-desc-container" section of index page, so that elements layer and not stack. | Jinyi | Open
2021-03-08 | 5 | Look into evolving index page to include links to Flights, Hotels, and Rentals for each destination. | Tamika | Open
2021-03-08 | 6 | Bring in contact page from initial project and re-design it to fit current design and feel of overall site. | Oswaldo | Open
2021-03-08 | 7 | Design and develop About Page for the Travel Canada site ensuring fit with overall theme of site. | Jonn | Open
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24